## Components
Honda RA621H – F1 Car Assembly Component Dataset
Power Unit: Honda RA621H (2021) ¦ Ref: Red Bull RB16B ¦ Driver: Max Verstappen – WDC 2021
Component ID | Component Name | Subsystem | Depends On (IDs) | Duration (hrs) | Is Critical Path | Weight (kg) | Material | Notes
C001 | V6 Cylinder Block (1.6L 90° Bank) | ICE – Internal Combustion Engine |  | 48 | ✓ CRITICAL | 12 | Cast Aluminium Alloy | 80mm bore, 90° bank angle per FIA regs. K-Plating applied (Kumamoto method) to bore surface
C002 | Crankshaft | ICE – Internal Combustion Engine | C001 | 24 | ✓ CRITICAL | 3.8 | Forged Steel | Connects to MGU-K via gear. Must balance torsional resonance (key failure mode 2015–2017)
C003 | Connecting Rods (x6) | ICE – Internal Combustion Engine | C001,C002 | 12 | ✓ CRITICAL | 0.9 | Titanium Alloy | Ultra-lightweight; 6 cylinders, each 150g. Tolerance <0.01mm
C004 | Pistons (x6) | ICE – Internal Combustion Engine | C001,C003 | 16 | ✓ CRITICAL | 0.6 | Forged Aluminium / Steel Crown | 3D-printed steel pistons (additive mfg) used from RA620H 2020. Complex internal ribbing
C005 | Piston Rings (x18) | ICE – Internal Combustion Engine | C004 | 4 | — | 0.1 | Chrome-Molybdenum Steel | 3 rings per piston; K-Plating bore reduces ring wear at high combustion pressure
C006 | Cylinder Head (x2 banks) | ICE – Internal Combustion Engine | C001,C004 | 36 | ✓ CRITICAL | 4.5 | Aluminium Alloy | 32° valve angle, flat-top combustion chamber for rapid combustion (RA621H 2021 redesign)
C007 | Intake Valves (x12) | ICE – Internal Combustion Engine | C006 | 8 | — | 0.05 | Titanium Alloy | 2 intake valves per cylinder. Minimum stem diameter 5mm per FIA regs
C008 | Exhaust Valves (x12) | ICE – Internal Combustion Engine | C006 | 8 | — | 0.06 | Inconel 713 | High-temp alloy; exhaust exits outside bank (per regs). Feeds turbine
C009 | Camshafts (x4) | ICE – Internal Combustion Engine | C006,C007,C008 | 14 | ✓ CRITICAL | 0.8 | Case-Hardened Steel | 2 DOHC per bank. Drives valve timing. Pneumatic valve springs (not mechanical)
C010 | Valve Actuation – Pneumatic System | ICE – Internal Combustion Engine | C009 | 6 | — | 0.4 | Titanium / Stainless Steel | Replaces coil springs; enables 20,000+ rpm without valve float
C011 | Engine Block Lower Casing | ICE – Internal Combustion Engine | C001,C002 | 10 | — | 5 | Cast Aluminium | Structural load path for PU mounting to gearbox
C012 | Direct Injection System (x6 injectors) | ICE – Internal Combustion Engine | C006 | 8 | ✓ CRITICAL | 0.3 | Stainless Steel / Piezo | Max injection pressure 500 bar per FIA regs. Critical for new combustion process (2019+)
C013 | Ignition System (x6 coils + spark plugs) | ICE – Internal Combustion Engine | C006,C012 | 4 | — | 0.2 | Iridium / Copper Core | Synchronised with MGU-H energy recovery for combustion efficiency
C014 | Exhaust Manifold (equal-length runners) | ICE – Internal Combustion Engine | C008 | 20 | ✓ CRITICAL | 2.1 | Inconel 625 | Individual equal-length runners reworked RA617H+. Feeds turbine efficiently
C015 | Engine Assembly & Bench Calibration | ICE – Internal Combustion Engine | C001,C002,C003,C004,C005,C006,C007,C008,C009,C010,C011,C012,C013,C014 | 36 | ✓ CRITICAL | — | — | Full ICE assembly + dyno calibration at Sakura HRC facility
C016 | Turbine Housing | Turbocharger System | C014 | 20 | ✓ CRITICAL | 1.8 | Inconel (3D-printed) | Additive manufactured from 2020. Rear-projecting layout (RA617H+ redesign)
C017 | Turbine Blades / Wheel | Turbocharger System | C016 | 16 | ✓ CRITICAL | 0.4 | Nickel Superalloy | 3D complex blade geometry for high efficiency. HondaJet gas turbine knowledge applied
C018 | Compressor Housing | Turbocharger System |  | 18 | ✓ CRITICAL | 1.2 | Aluminium Alloy | Front-projecting (RA617H redesign). Freed from V-bank; larger size for higher airflow
C019 | Compressor Wheel | Turbocharger System | C018 | 14 | ✓ CRITICAL | 0.3 | Titanium Alloy | Wide pressure ratio coverage. Redesigned 2019 French GP for efficiency across full range
C020 | Turbo Shaft (MGU-H Drive Shaft) | Turbocharger System | C017,C019 | 10 | ✓ CRITICAL | 0.2 | High-strength Steel | Connects turbine-MGU-H-compressor. Changed to longer shaft 2017 for turbine efficiency
C021 | Turbo Bearing Assembly | Turbocharger System | C020 | 8 | — | 0.1 | Ceramic / Steel (oil-lubricated) | Changed greased→oil lubrication RA618H. Pressurized chamber to seal oil at 100k+ rpm
C022 | Charge Air Cooler (Inter-cooler) | Turbocharger System | C019,C018 | 12 | — | 1.5 | Aluminium | Cools compressed air before intake. Compact design per McLaren era (RA615H)
C023 | Wastegate Actuator | Turbocharger System | C016 | 4 | — | 0.2 | Stainless Steel | Bypasses excess exhaust; less critical with MGU-H managing boost
C024 | Turbocharger Sub-Assembly | Turbocharger System | C016,C017,C018,C019,C020,C021,C022,C023 | 12 | ✓ CRITICAL | — | — | Full turbo unit assembled before mating with MGU-H
C025 | MGU-H Rotor & Magnet Assembly | Hybrid – MGU-H |  | 20 | ✓ CRITICAL | 1.5 | High-flux Neodymium Magnets | RA621H: high magnetic flux density magnets + high thermal conductivity insulators
C026 | MGU-H Stator Windings | Hybrid – MGU-H | C025 | 16 | ✓ CRITICAL | 1.2 | Copper / Insulated Litz Wire | Converts shaft rotation→electricity (gen mode) or electricity→shaft (motor mode)
C027 | MGU-H Housing | Hybrid – MGU-H | C025,C026 | 14 | ✓ CRITICAL | 0.8 | Inconel (3D-printed) | Pressurized chamber for oil sealing. Sandwiched between turbine & compressor
C028 | MGU-H Cooling Circuit | Hybrid – MGU-H | C027 | 8 | — | 0.3 | Aluminium / Polymer | Maintains thermal limits at 125,000 rpm. Critical for RA621H output targets
C029 | MGU-H Assembly (complete) | Hybrid – MGU-H | C024,C025,C026,C027,C028 | 10 | ✓ CRITICAL | — | — | Mated to turbo shaft. Min weight 4kg. Power ~90-100 kW at 125,000 rpm
C030 | MGU-K Rotor & Magnet Assembly | Hybrid – MGU-K |  | 18 | ✓ CRITICAL | 2 | High-flux Neodymium Magnets | RA621H gear ratio change allows energy recovery at even lower engine speeds
C031 | MGU-K Stator Windings | Hybrid – MGU-K | C030 | 14 | ✓ CRITICAL | 1.8 | Copper / Litz Wire | Max output 120 kW / 200 Nm per FIA regs. Housing rigidity increased RA621H for vibration
C032 | MGU-K Gear Interface | Hybrid – MGU-K | C030,C031,C002 | 10 | ✓ CRITICAL | 0.5 | Case-hardened Steel Gears | Connects MGU-K to crankshaft. Shaft weakness (spring design) resolved torsional resonance
C033 | MGU-K Housing & Bearing | Hybrid – MGU-K | C030,C031 | 8 | — | 1 | Aluminium / Steel Bearings | Bearing support changed 2018; radial load allowance increased after bench-vs-installed failure
C034 | MGU-K Assembly (complete) | Hybrid – MGU-K | C030,C031,C032,C033 | 8 | ✓ CRITICAL | — | — | Connected to crankshaft gear. Provides up to 160 bhp ERS deployment
C035 | Li-Ion Battery Cells (ES) | Energy Store (ES) |  | 20 | ✓ CRITICAL | 10 | Lithium-Ion Polymer | High-performance specialist battery. Max 4 MJ deploy per lap / 2 MJ recover via MGU-K
C036 | Battery Management System (BMS) | Energy Store (ES) | C035 | 12 | ✓ CRITICAL | 0.5 | PCB / Custom ASIC | Manages thermal limits, charge/discharge rate, and voltage balance
C037 | ES Thermal Management | Energy Store (ES) | C035,C036 | 10 | — | 1.2 | Aluminium / Cooling Plates | Fast charge/discharge generates extreme heat. Integrated liquid cooling
C038 | Power Electronics / Inverter Unit | Energy Store (ES) | C029,C034,C035,C036,C037 | 16 | ✓ CRITICAL | 2 | Silicon Carbide (SiC) MOSFETs | Bi-directional AC/DC converters. Enables direct MGU-H→MGU-K routing bypassing battery
C039 | Dry-Sump Oil Tank | Lubrication System |  | 6 | — | 1.5 | Carbon Fibre / Aluminium | Low-profile for CoG; separated from engine block
C040 | Oil Pump & Scavenge Pumps | Lubrication System | C039 | 8 | ✓ CRITICAL | 0.8 | Machined Aluminium | Multiple scavenge pumps for high-G cornering oil control
C041 | Oil Cooler | Lubrication System | C039,C040 | 6 | — | 0.9 | Aluminium | Keeps oil at optimal viscosity; integrated into cooling circuit
C042 | Oil Filter & Pressure Regulators | Lubrication System | C040 | 4 | — | 0.2 | Stainless Steel | Prevents particulate damage. Critical for engine life management (2–3 races per PU)
C043 | Water Pump (Electric) | Cooling System |  | 6 | — | 0.6 | Machined Aluminium / Impeller | Electrically driven for independent cooling control
C044 | Radiators (x2 side pods) | Cooling System | C043 | 10 | — | 2.4 | Aluminium Core / Carbon Ducts | Side pod mounted. Compact design to minimise aerodynamic drag
C045 | Coolant Hoses & Distribution Lines | Cooling System | C043,C044 | 6 | — | 0.5 | Silicone / Composite | Routes coolant to ICE, MGU-K, ES. High-temp rated >180°C
C046 | Fuel Tank (FIA Bladder, ~100kg capacity) | Fuel System |  | 12 | — | 4 | FIA Kevlar Bladder | Crash-tested safety bladder. Positioned centrally for weight distribution
C047 | Fuel Pump & Pressure Regulator | Fuel System | C046 | 6 | ✓ CRITICAL | 0.4 | Stainless Steel / Titanium | Must supply 100 kg/hr max flow rate (FIA regulated). High-pressure to injectors
C048 | Fuel Filter & Lines | Fuel System | C046,C047 | 4 | — | 0.3 | Stainless / PTFE-lined | Prevents injector damage. Zero tolerance for particulate contamination
C049 | Engine Control Unit (ECU) – FIA Standard | Electronics & Control |  | 8 | ✓ CRITICAL | 0.9 | Custom ASIC / PCB | FIA mandated McLaren TAG-320 ECU. Controls all PU functions + energy management
C050 | Wiring Loom (PU section) | Electronics & Control | C049 | 16 | — | 3.5 | Shielded Copper / PTFE | ~1 km total wiring in F1 car. PU section manages MGU-H, MGU-K, ES, ICE signals
C051 | Sensors Array (temp/pressure/speed – PU) | Electronics & Control | C049,C050 | 10 | — | 0.6 | Piezoelectric / Thermocouple | 100s of sensors. Data telemetered live to Sakura HRC during race
C052 | Carbon Fibre Monocoque (Survival Cell) | Chassis & Monocoque |  | 96 | ✓ CRITICAL | 35 | Carbon Fibre Composite (CFRP) | Autoclave-cured CFRP. Accuracy ±0.05mm. Integrates survival cell, fuel tank cavity
C053 | Roll Hoop (Halo + Main) | Chassis & Monocoque | C052 | 24 | ✓ CRITICAL | 7.5 | Carbon Fibre / Titanium | Halo (titanium, 7.5mm thick) mandatory since 2018. Withstands 125 kN load
C054 | Ballast Weights | Chassis & Monocoque | C052 | 4 | — | 12 | Tungsten | Adjust CoG and minimum weight (798 kg with driver 2021). Critical for balance
C055 | Mounting Points – Engine & Gearbox | Chassis & Monocoque | C052,C015 | 8 | ✓ CRITICAL | — | CFRP insert / Ti bolts | Engine stressed member of chassis. PU acts as structural element
C056 | Front Upper Wishbone (x2) | Suspension – Front | C052 | 12 | — | 0.6 | Carbon Fibre | Double wishbone geometry. Push-rod actuation layout front
C057 | Front Lower Wishbone (x2) | Suspension – Front | C052 | 12 | — | 0.7 | Carbon Fibre | Aero-shaped cross-section to manage underfloor airflow
C058 | Front Push-Rod (x2) | Suspension – Front | C056,C057 | 6 | — | 0.2 | Carbon Fibre | Transmits suspension loads to inboard rocker
C059 | Front Rockers & Torsion Bars (x2) | Suspension – Front | C058 | 8 | — | 0.4 | Titanium Alloy | Adjustable setup for different circuit characteristics (stiff vs compliant)
C060 | Front Upright & Hub Assembly (x2) | Suspension – Front | C056,C057 | 14 | — | 1.8 | Billet Aluminium / Ti | Houses wheel bearing; interfaces with brake caliper and wheel
C061 | Front Anti-Roll Bar | Suspension – Front | C059 | 4 | — | 0.1 | Carbon Fibre | Controls body roll in cornering. Adjustable stiffness
C062 | Rear Upper Wishbone (x2) | Suspension – Rear | C055 | 12 | — | 0.7 | Carbon Fibre | Pull-rod rear actuation layout (RB16B). Lower CoG benefit
C063 | Rear Lower Wishbone (x2) | Suspension – Rear | C055 | 12 | — | 0.8 | Carbon Fibre | Designed around gearbox casing geometry
C064 | Rear Pull-Rod (x2) | Suspension – Rear | C062,C063 | 6 | — | 0.2 | Carbon Fibre | Loads fed down to gearbox-mounted damper unit
C065 | Rear Rockers & Damper Unit (x2) | Suspension – Rear | C064 | 10 | — | 0.5 | Titanium / Aluminium | Gearbox integrated. Complex multi-element damper
C066 | Rear Upright & Hub Assembly (x2) | Suspension – Rear | C062,C063 | 14 | — | 2 | Billet Aluminium / Ti | Interfaces with brake-by-wire system and driveshaft
C067 | Rear Anti-Roll Bar | Suspension – Rear | C065 | 4 | — | 0.1 | Carbon Fibre | Adjustable; key setup parameter for rear stability
C068 | Front Wing Mainplane | Aerodynamics – Front | C052 | 40 | ✓ CRITICAL | 5.5 | Carbon Fibre Composite | Most complex aero part. 4–6 weeks design+test. Multiple elements for downforce
C069 | Front Wing Flap Cascade Elements (x4) | Aerodynamics – Front | C068 | 20 | — | 1.2 | Carbon Fibre Composite | Adjustable for downforce level. Replaced each race weekend after contact risk
C070 | Nose Cone (crash structure) | Aerodynamics – Front | C068,C052 | 24 | ✓ CRITICAL | 3 | Carbon Fibre / Nomex Honeycomb | FIA crash-tested. Sacrificial structure. Shaped for aerodynamic entry
C071 | Bargeboard / Vane Package | Aerodynamics – Front | C052,C070 | 28 | — | 1.5 | Carbon Fibre Composite | Directs airflow to sidepods and floor. High-update rate component across season
C072 | Floor & Skid Block Assembly | Aerodynamics – Front | C052 | 36 | ✓ CRITICAL | 8 | Carbon Fibre / Plank (hardwood) | Generates significant ground effect downforce. FIA-regulated 10mm wooden plank
C073 | Rear Wing Mainplane | Aerodynamics – Rear | C055 | 30 | ✓ CRITICAL | 4 | Carbon Fibre Composite | Fixed structure. Angle adjusted per circuit (Monaco high vs Monza low downforce)
C074 | DRS Flap (Drag Reduction System) | Aerodynamics – Rear | C073 | 12 | — | 0.5 | Carbon Fibre Composite | FIA-controlled actuation. Opens on designated DRS zones to reduce drag ~20%
C075 | Beam Wing | Aerodynamics – Rear | C073,C055 | 14 | — | 1 | Carbon Fibre Composite | Lower secondary element below rear wing. Seals diffuser exit flow
C076 | Diffuser | Aerodynamics – Rear | C072,C055 | 28 | ✓ CRITICAL | 3.5 | Carbon Fibre Composite | Accelerates underfloor airflow exit. Critical ground-effect component
C077 | Gearbox Casing (8-speed semi-auto) | Gearbox & Drivetrain | C055 | 48 | ✓ CRITICAL | 18 | Carbon Fibre / Titanium | 8-speed seamless shift. Acts as structural rear suspension carrier (RB16B)
C078 | Gear Stack & Selector Mechanism | Gearbox & Drivetrain | C077 | 32 | ✓ CRITICAL | 4.5 | Case-hardened Steel | Seamless shift: next gear pre-engaged. <5ms shift time. Barrel cam selection
C079 | Differential | Gearbox & Drivetrain | C077,C078 | 14 | ✓ CRITICAL | 1.8 | Titanium / Steel | Multi-plate clutch diff. Adjustable ramp angles for traction balance
C080 | Driveshafts (x2) | Gearbox & Drivetrain | C079,C066 | 10 | — | 1.2 | Carbon Fibre / CV Joints Ti | Constant-velocity joints for suspension articulation + high-torque delivery
C081 | Clutch Assembly | Gearbox & Drivetrain | C077,C034 | 8 | ✓ CRITICAL | 0.6 | Carbon-Carbon Multi-plate | Paddle-operated. Must accommodate MGU-K torque delivery during race start
C082 | Carbon Brake Discs – Front (x2) | Braking System | C060 | 16 | ✓ CRITICAL | 1 | Carbon-Carbon Composite | ~1000°C operational temp. 28mm thick. Glowing red during braking visible in races
C083 | Carbon Brake Discs – Rear (x2) | Braking System | C066 | 14 | — | 0.9 | Carbon-Carbon Composite | Brake-by-wire rear (coordinates with MGU-K regen braking)
C084 | Brake Calipers – Front (x2) | Braking System | C060,C082 | 10 | — | 1.4 | Billet Aluminium (Brembo) | 6-piston monoblock caliper. Custom made per team specification
C085 | Brake Calipers – Rear (x2) | Braking System | C066,C083 | 10 | — | 1.2 | Billet Aluminium (Brembo) | Integrated brake-by-wire actuator for regen coordination
C086 | Brake Ducts & Cooling Scoops (x4) | Braking System | C082,C083,C084,C085 | 8 | — | 0.6 | Carbon Fibre | Circuit-specific. Minimal cooling (low drag) at Monza; maximum at Monaco
C087 | Master Cylinders & Brake-by-Wire ECU | Braking System | C049,C083,C085 | 10 | ✓ CRITICAL | 0.8 | Aluminium / Electronics | Blends hydraulic front brakes with electric rear braking from MGU-K
C088 | Forged Magnesium Wheels – Front (x2) | Wheels & Tyres | C060 | 8 | — | 2 | Forged Magnesium Alloy | 18-inch (from 2022 regs). Centre-lock. OZ Racing supplied
C089 | Forged Magnesium Wheels – Rear (x2) | Wheels & Tyres | C066 | 8 | — | 2.5 | Forged Magnesium Alloy | Wider than front. Must withstand 12,000 Nm under heavy acceleration
C090 | Pirelli P Zero Tyres – set (4) | Wheels & Tyres | C088,C089 | 2 | — | 10 | Rubber / Kevlar Belts | 5 compounds: C1–C5. Teams receive 13 sets per race weekend (2021 regs)
C091 | Halo Titanium Structure | Cockpit & Safety | C052 | 16 | ✓ CRITICAL | 7.5 | Grade 5 Titanium (6Al-4V) | Mandatory since 2018. 125 kN frontal load requirement. Saved Leclerc, Zhou lives
C092 | Driver Seat (custom moulded) | Cockpit & Safety | C052 | 12 | — | 3 | Carbon Fibre | Moulded to specific driver. Removes in <5s for rescue. HANS device compatible
C093 | Steering Wheel & Column | Cockpit & Safety | C052,C049 | 20 | ✓ CRITICAL | 1.5 | Carbon Fibre / Electronics | ~25 buttons, rotary dials. Detachable; driver must exit with it per FIA regs
C094 | Safety Harness (6-point) | Cockpit & Safety | C052,C092 | 2 | — | 0.5 | FIA-rated Polyester Webbing | 6-point HANS-compatible. Replaced each race event
C095 | Fire Suppression System | Cockpit & Safety | C052 | 4 | — | 1 | AFFF / Halon Cylinder | Cockpit + engine bay nozzles. Driver-activated or auto-trigger
C096 | Drink System & Helmet Cooling | Cockpit & Safety | C052 | 3 | — | 0.4 | Food-grade Tubing / Pump | Delivers electrolyte drink + cooling air inside helmet during race
C097 | PU Installation into Chassis | Final Assembly | C015,C029,C034,C038,C052,C055 | 24 | ✓ CRITICAL | — | — | Honda RA621H power unit (ICE+MGU-H+MGU-K+ES+inverter) installed as structural member
C098 | Gearbox Mating to PU | Final Assembly | C097,C077,C078,C079,C081 | 12 | ✓ CRITICAL | — | — | Gearbox bolted to PU rear face. Rear suspension carrier now active
C099 | Suspension Assembly – Full Car | Final Assembly | C098,C056,C057,C058,C059,C060,C061,C062,C063,C064,C065,C066,C067 | 16 | ✓ CRITICAL | — | — | Front and rear suspension installed. Geometry set to base setup
C100 | Aero & Bodywork Installation | Final Assembly | C099,C068,C069,C070,C071,C072,C073,C074,C075,C076 | 20 | ✓ CRITICAL | — | — | All carbon bodywork, wings, floor fitted. Circuit-specific aero configuration
C101 | Brakes, Wheels & Tyre Fitting | Final Assembly | C099,C082,C083,C084,C085,C086,C087,C088,C089,C090 | 8 | ✓ CRITICAL | — | — | Braking system installed. Brake-by-wire calibrated. Tyres fitted and pressured
C102 | Cockpit, Safety & Electronics Commissioning | Final Assembly | C099,C091,C092,C093,C094,C095,C096,C050,C051 | 10 | ✓ CRITICAL | — | — | Driver seat, halo, steering, safety systems installed. ECU flashed with race software
C103 | Full Car Systems Check & Sign-Off | Final Assembly | C097,C098,C099,C100,C101,C102 | 8 | ✓ CRITICAL | — | — | Full car fired up, all PU systems verified, weight/CoG measured. FIA scrutineering ready

## Dependency_Edges
DAG Edge List – Honda RA621H Assembly Dependencies
Each row = one directed edge: FROM (prerequisite) → TO (dependent). Use this for DAG & Topological Sort implementation.
Edge ID | FROM (Prerequisite ID) | FROM Name | TO (Dependent ID) | TO Name | Edge Weight (hrs)
E001 | C001 | V6 Cylinder Block (1.6L 90° Bank) | C002 | Crankshaft | 48
E002 | C001 | V6 Cylinder Block (1.6L 90° Bank) | C003 | Connecting Rods (x6) | 48
E003 | C002 | Crankshaft | C003 | Connecting Rods (x6) | 24
E004 | C001 | V6 Cylinder Block (1.6L 90° Bank) | C004 | Pistons (x6) | 48
E005 | C003 | Connecting Rods (x6) | C004 | Pistons (x6) | 12
E006 | C004 | Pistons (x6) | C005 | Piston Rings (x18) | 16
E007 | C001 | V6 Cylinder Block (1.6L 90° Bank) | C006 | Cylinder Head (x2 banks) | 48
E008 | C004 | Pistons (x6) | C006 | Cylinder Head (x2 banks) | 16
E009 | C006 | Cylinder Head (x2 banks) | C007 | Intake Valves (x12) | 36
E010 | C006 | Cylinder Head (x2 banks) | C008 | Exhaust Valves (x12) | 36
E011 | C006 | Cylinder Head (x2 banks) | C009 | Camshafts (x4) | 36
E012 | C007 | Intake Valves (x12) | C009 | Camshafts (x4) | 8
E013 | C008 | Exhaust Valves (x12) | C009 | Camshafts (x4) | 8
E014 | C009 | Camshafts (x4) | C010 | Valve Actuation – Pneumatic System | 14
E015 | C001 | V6 Cylinder Block (1.6L 90° Bank) | C011 | Engine Block Lower Casing | 48
E016 | C002 | Crankshaft | C011 | Engine Block Lower Casing | 24
E017 | C006 | Cylinder Head (x2 banks) | C012 | Direct Injection System (x6 injectors) | 36
E018 | C006 | Cylinder Head (x2 banks) | C013 | Ignition System (x6 coils + spark plugs) | 36
E019 | C012 | Direct Injection System (x6 injectors) | C013 | Ignition System (x6 coils + spark plugs) | 8
E020 | C008 | Exhaust Valves (x12) | C014 | Exhaust Manifold (equal-length runners) | 8
E021 | C001 | V6 Cylinder Block (1.6L 90° Bank) | C015 | Engine Assembly & Bench Calibration | 48
E022 | C002 | Crankshaft | C015 | Engine Assembly & Bench Calibration | 24
E023 | C003 | Connecting Rods (x6) | C015 | Engine Assembly & Bench Calibration | 12
E024 | C004 | Pistons (x6) | C015 | Engine Assembly & Bench Calibration | 16
E025 | C005 | Piston Rings (x18) | C015 | Engine Assembly & Bench Calibration | 4
E026 | C006 | Cylinder Head (x2 banks) | C015 | Engine Assembly & Bench Calibration | 36
E027 | C007 | Intake Valves (x12) | C015 | Engine Assembly & Bench Calibration | 8
E028 | C008 | Exhaust Valves (x12) | C015 | Engine Assembly & Bench Calibration | 8
E029 | C009 | Camshafts (x4) | C015 | Engine Assembly & Bench Calibration | 14
E030 | C010 | Valve Actuation – Pneumatic System | C015 | Engine Assembly & Bench Calibration | 6
E031 | C011 | Engine Block Lower Casing | C015 | Engine Assembly & Bench Calibration | 10
E032 | C012 | Direct Injection System (x6 injectors) | C015 | Engine Assembly & Bench Calibration | 8
E033 | C013 | Ignition System (x6 coils + spark plugs) | C015 | Engine Assembly & Bench Calibration | 4
E034 | C014 | Exhaust Manifold (equal-length runners) | C015 | Engine Assembly & Bench Calibration | 20
E035 | C014 | Exhaust Manifold (equal-length runners) | C016 | Turbine Housing | 20
E036 | C016 | Turbine Housing | C017 | Turbine Blades / Wheel | 20
E037 | C018 | Compressor Housing | C019 | Compressor Wheel | 18
E038 | C017 | Turbine Blades / Wheel | C020 | Turbo Shaft (MGU-H Drive Shaft) | 16
E039 | C019 | Compressor Wheel | C020 | Turbo Shaft (MGU-H Drive Shaft) | 14
E040 | C020 | Turbo Shaft (MGU-H Drive Shaft) | C021 | Turbo Bearing Assembly | 10
E041 | C019 | Compressor Wheel | C022 | Charge Air Cooler (Inter-cooler) | 14
E042 | C018 | Compressor Housing | C022 | Charge Air Cooler (Inter-cooler) | 18
E043 | C016 | Turbine Housing | C023 | Wastegate Actuator | 20
E044 | C016 | Turbine Housing | C024 | Turbocharger Sub-Assembly | 20
E045 | C017 | Turbine Blades / Wheel | C024 | Turbocharger Sub-Assembly | 16
E046 | C018 | Compressor Housing | C024 | Turbocharger Sub-Assembly | 18
E047 | C019 | Compressor Wheel | C024 | Turbocharger Sub-Assembly | 14
E048 | C020 | Turbo Shaft (MGU-H Drive Shaft) | C024 | Turbocharger Sub-Assembly | 10
E049 | C021 | Turbo Bearing Assembly | C024 | Turbocharger Sub-Assembly | 8
E050 | C022 | Charge Air Cooler (Inter-cooler) | C024 | Turbocharger Sub-Assembly | 12
E051 | C023 | Wastegate Actuator | C024 | Turbocharger Sub-Assembly | 4
E052 | C025 | MGU-H Rotor & Magnet Assembly | C026 | MGU-H Stator Windings | 20
E053 | C025 | MGU-H Rotor & Magnet Assembly | C027 | MGU-H Housing | 20
E054 | C026 | MGU-H Stator Windings | C027 | MGU-H Housing | 16
E055 | C027 | MGU-H Housing | C028 | MGU-H Cooling Circuit | 14
E056 | C024 | Turbocharger Sub-Assembly | C029 | MGU-H Assembly (complete) | 12
E057 | C025 | MGU-H Rotor & Magnet Assembly | C029 | MGU-H Assembly (complete) | 20
E058 | C026 | MGU-H Stator Windings | C029 | MGU-H Assembly (complete) | 16
E059 | C027 | MGU-H Housing | C029 | MGU-H Assembly (complete) | 14
E060 | C028 | MGU-H Cooling Circuit | C029 | MGU-H Assembly (complete) | 8
E061 | C030 | MGU-K Rotor & Magnet Assembly | C031 | MGU-K Stator Windings | 18
E062 | C030 | MGU-K Rotor & Magnet Assembly | C032 | MGU-K Gear Interface | 18
E063 | C031 | MGU-K Stator Windings | C032 | MGU-K Gear Interface | 14
E064 | C002 | Crankshaft | C032 | MGU-K Gear Interface | 24
E065 | C030 | MGU-K Rotor & Magnet Assembly | C033 | MGU-K Housing & Bearing | 18
E066 | C031 | MGU-K Stator Windings | C033 | MGU-K Housing & Bearing | 14
E067 | C030 | MGU-K Rotor & Magnet Assembly | C034 | MGU-K Assembly (complete) | 18
E068 | C031 | MGU-K Stator Windings | C034 | MGU-K Assembly (complete) | 14
E069 | C032 | MGU-K Gear Interface | C034 | MGU-K Assembly (complete) | 10
E070 | C033 | MGU-K Housing & Bearing | C034 | MGU-K Assembly (complete) | 8
E071 | C035 | Li-Ion Battery Cells (ES) | C036 | Battery Management System (BMS) | 20
E072 | C035 | Li-Ion Battery Cells (ES) | C037 | ES Thermal Management | 20
E073 | C036 | Battery Management System (BMS) | C037 | ES Thermal Management | 12
E074 | C029 | MGU-H Assembly (complete) | C038 | Power Electronics / Inverter Unit | 10
E075 | C034 | MGU-K Assembly (complete) | C038 | Power Electronics / Inverter Unit | 8
E076 | C035 | Li-Ion Battery Cells (ES) | C038 | Power Electronics / Inverter Unit | 20
E077 | C036 | Battery Management System (BMS) | C038 | Power Electronics / Inverter Unit | 12
E078 | C037 | ES Thermal Management | C038 | Power Electronics / Inverter Unit | 10
E079 | C039 | Dry-Sump Oil Tank | C040 | Oil Pump & Scavenge Pumps | 6
E080 | C039 | Dry-Sump Oil Tank | C041 | Oil Cooler | 6
E081 | C040 | Oil Pump & Scavenge Pumps | C041 | Oil Cooler | 8
E082 | C040 | Oil Pump & Scavenge Pumps | C042 | Oil Filter & Pressure Regulators | 8
E083 | C043 | Water Pump (Electric) | C044 | Radiators (x2 side pods) | 6
E084 | C043 | Water Pump (Electric) | C045 | Coolant Hoses & Distribution Lines | 6
E085 | C044 | Radiators (x2 side pods) | C045 | Coolant Hoses & Distribution Lines | 10
E086 | C046 | Fuel Tank (FIA Bladder, ~100kg capacity) | C047 | Fuel Pump & Pressure Regulator | 12
E087 | C046 | Fuel Tank (FIA Bladder, ~100kg capacity) | C048 | Fuel Filter & Lines | 12
E088 | C047 | Fuel Pump & Pressure Regulator | C048 | Fuel Filter & Lines | 6
E089 | C049 | Engine Control Unit (ECU) – FIA Standard | C050 | Wiring Loom (PU section) | 8
E090 | C049 | Engine Control Unit (ECU) – FIA Standard | C051 | Sensors Array (temp/pressure/speed – PU) | 8
E091 | C050 | Wiring Loom (PU section) | C051 | Sensors Array (temp/pressure/speed – PU) | 16
E092 | C052 | Carbon Fibre Monocoque (Survival Cell) | C053 | Roll Hoop (Halo + Main) | 96
E093 | C052 | Carbon Fibre Monocoque (Survival Cell) | C054 | Ballast Weights | 96
E094 | C052 | Carbon Fibre Monocoque (Survival Cell) | C055 | Mounting Points – Engine & Gearbox | 96
E095 | C015 | Engine Assembly & Bench Calibration | C055 | Mounting Points – Engine & Gearbox | 36
E096 | C052 | Carbon Fibre Monocoque (Survival Cell) | C056 | Front Upper Wishbone (x2) | 96
E097 | C052 | Carbon Fibre Monocoque (Survival Cell) | C057 | Front Lower Wishbone (x2) | 96
E098 | C056 | Front Upper Wishbone (x2) | C058 | Front Push-Rod (x2) | 12
E099 | C057 | Front Lower Wishbone (x2) | C058 | Front Push-Rod (x2) | 12
E100 | C058 | Front Push-Rod (x2) | C059 | Front Rockers & Torsion Bars (x2) | 6
E101 | C056 | Front Upper Wishbone (x2) | C060 | Front Upright & Hub Assembly (x2) | 12
E102 | C057 | Front Lower Wishbone (x2) | C060 | Front Upright & Hub Assembly (x2) | 12
E103 | C059 | Front Rockers & Torsion Bars (x2) | C061 | Front Anti-Roll Bar | 8
E104 | C055 | Mounting Points – Engine & Gearbox | C062 | Rear Upper Wishbone (x2) | 8
E105 | C055 | Mounting Points – Engine & Gearbox | C063 | Rear Lower Wishbone (x2) | 8
E106 | C062 | Rear Upper Wishbone (x2) | C064 | Rear Pull-Rod (x2) | 12
E107 | C063 | Rear Lower Wishbone (x2) | C064 | Rear Pull-Rod (x2) | 12
E108 | C064 | Rear Pull-Rod (x2) | C065 | Rear Rockers & Damper Unit (x2) | 6
E109 | C062 | Rear Upper Wishbone (x2) | C066 | Rear Upright & Hub Assembly (x2) | 12
E110 | C063 | Rear Lower Wishbone (x2) | C066 | Rear Upright & Hub Assembly (x2) | 12
E111 | C065 | Rear Rockers & Damper Unit (x2) | C067 | Rear Anti-Roll Bar | 10
E112 | C052 | Carbon Fibre Monocoque (Survival Cell) | C068 | Front Wing Mainplane | 96
E113 | C068 | Front Wing Mainplane | C069 | Front Wing Flap Cascade Elements (x4) | 40
E114 | C068 | Front Wing Mainplane | C070 | Nose Cone (crash structure) | 40
E115 | C052 | Carbon Fibre Monocoque (Survival Cell) | C070 | Nose Cone (crash structure) | 96
E116 | C052 | Carbon Fibre Monocoque (Survival Cell) | C071 | Bargeboard / Vane Package | 96
E117 | C070 | Nose Cone (crash structure) | C071 | Bargeboard / Vane Package | 24
E118 | C052 | Carbon Fibre Monocoque (Survival Cell) | C072 | Floor & Skid Block Assembly | 96
E119 | C055 | Mounting Points – Engine & Gearbox | C073 | Rear Wing Mainplane | 8
E120 | C073 | Rear Wing Mainplane | C074 | DRS Flap (Drag Reduction System) | 30
E121 | C073 | Rear Wing Mainplane | C075 | Beam Wing | 30
E122 | C055 | Mounting Points – Engine & Gearbox | C075 | Beam Wing | 8
E123 | C072 | Floor & Skid Block Assembly | C076 | Diffuser | 36
E124 | C055 | Mounting Points – Engine & Gearbox | C076 | Diffuser | 8
E125 | C055 | Mounting Points – Engine & Gearbox | C077 | Gearbox Casing (8-speed semi-auto) | 8
E126 | C077 | Gearbox Casing (8-speed semi-auto) | C078 | Gear Stack & Selector Mechanism | 48
E127 | C077 | Gearbox Casing (8-speed semi-auto) | C079 | Differential | 48
E128 | C078 | Gear Stack & Selector Mechanism | C079 | Differential | 32
E129 | C079 | Differential | C080 | Driveshafts (x2) | 14
E130 | C066 | Rear Upright & Hub Assembly (x2) | C080 | Driveshafts (x2) | 14
E131 | C077 | Gearbox Casing (8-speed semi-auto) | C081 | Clutch Assembly | 48
E132 | C034 | MGU-K Assembly (complete) | C081 | Clutch Assembly | 8
E133 | C060 | Front Upright & Hub Assembly (x2) | C082 | Carbon Brake Discs – Front (x2) | 14
E134 | C066 | Rear Upright & Hub Assembly (x2) | C083 | Carbon Brake Discs – Rear (x2) | 14
E135 | C060 | Front Upright & Hub Assembly (x2) | C084 | Brake Calipers – Front (x2) | 14
E136 | C082 | Carbon Brake Discs – Front (x2) | C084 | Brake Calipers – Front (x2) | 16
E137 | C066 | Rear Upright & Hub Assembly (x2) | C085 | Brake Calipers – Rear (x2) | 14
E138 | C083 | Carbon Brake Discs – Rear (x2) | C085 | Brake Calipers – Rear (x2) | 14
E139 | C082 | Carbon Brake Discs – Front (x2) | C086 | Brake Ducts & Cooling Scoops (x4) | 16
E140 | C083 | Carbon Brake Discs – Rear (x2) | C086 | Brake Ducts & Cooling Scoops (x4) | 14
E141 | C084 | Brake Calipers – Front (x2) | C086 | Brake Ducts & Cooling Scoops (x4) | 10
E142 | C085 | Brake Calipers – Rear (x2) | C086 | Brake Ducts & Cooling Scoops (x4) | 10
E143 | C049 | Engine Control Unit (ECU) – FIA Standard | C087 | Master Cylinders & Brake-by-Wire ECU | 8
E144 | C083 | Carbon Brake Discs – Rear (x2) | C087 | Master Cylinders & Brake-by-Wire ECU | 14
E145 | C085 | Brake Calipers – Rear (x2) | C087 | Master Cylinders & Brake-by-Wire ECU | 10
E146 | C060 | Front Upright & Hub Assembly (x2) | C088 | Forged Magnesium Wheels – Front (x2) | 14
E147 | C066 | Rear Upright & Hub Assembly (x2) | C089 | Forged Magnesium Wheels – Rear (x2) | 14
E148 | C088 | Forged Magnesium Wheels – Front (x2) | C090 | Pirelli P Zero Tyres – set (4) | 8
E149 | C089 | Forged Magnesium Wheels – Rear (x2) | C090 | Pirelli P Zero Tyres – set (4) | 8
E150 | C052 | Carbon Fibre Monocoque (Survival Cell) | C091 | Halo Titanium Structure | 96
E151 | C052 | Carbon Fibre Monocoque (Survival Cell) | C092 | Driver Seat (custom moulded) | 96
E152 | C052 | Carbon Fibre Monocoque (Survival Cell) | C093 | Steering Wheel & Column | 96
E153 | C049 | Engine Control Unit (ECU) – FIA Standard | C093 | Steering Wheel & Column | 8
E154 | C052 | Carbon Fibre Monocoque (Survival Cell) | C094 | Safety Harness (6-point) | 96
E155 | C092 | Driver Seat (custom moulded) | C094 | Safety Harness (6-point) | 12
E156 | C052 | Carbon Fibre Monocoque (Survival Cell) | C095 | Fire Suppression System | 96
E157 | C052 | Carbon Fibre Monocoque (Survival Cell) | C096 | Drink System & Helmet Cooling | 96
E158 | C015 | Engine Assembly & Bench Calibration | C097 | PU Installation into Chassis | 36
E159 | C029 | MGU-H Assembly (complete) | C097 | PU Installation into Chassis | 10
E160 | C034 | MGU-K Assembly (complete) | C097 | PU Installation into Chassis | 8
E161 | C038 | Power Electronics / Inverter Unit | C097 | PU Installation into Chassis | 16
E162 | C052 | Carbon Fibre Monocoque (Survival Cell) | C097 | PU Installation into Chassis | 96
E163 | C055 | Mounting Points – Engine & Gearbox | C097 | PU Installation into Chassis | 8
E164 | C097 | PU Installation into Chassis | C098 | Gearbox Mating to PU | 24
E165 | C077 | Gearbox Casing (8-speed semi-auto) | C098 | Gearbox Mating to PU | 48
E166 | C078 | Gear Stack & Selector Mechanism | C098 | Gearbox Mating to PU | 32
E167 | C079 | Differential | C098 | Gearbox Mating to PU | 14
E168 | C081 | Clutch Assembly | C098 | Gearbox Mating to PU | 8
E169 | C098 | Gearbox Mating to PU | C099 | Suspension Assembly – Full Car | 12
E170 | C056 | Front Upper Wishbone (x2) | C099 | Suspension Assembly – Full Car | 12
E171 | C057 | Front Lower Wishbone (x2) | C099 | Suspension Assembly – Full Car | 12
E172 | C058 | Front Push-Rod (x2) | C099 | Suspension Assembly – Full Car | 6
E173 | C059 | Front Rockers & Torsion Bars (x2) | C099 | Suspension Assembly – Full Car | 8
E174 | C060 | Front Upright & Hub Assembly (x2) | C099 | Suspension Assembly – Full Car | 14
E175 | C061 | Front Anti-Roll Bar | C099 | Suspension Assembly – Full Car | 4
E176 | C062 | Rear Upper Wishbone (x2) | C099 | Suspension Assembly – Full Car | 12
E177 | C063 | Rear Lower Wishbone (x2) | C099 | Suspension Assembly – Full Car | 12
E178 | C064 | Rear Pull-Rod (x2) | C099 | Suspension Assembly – Full Car | 6
E179 | C065 | Rear Rockers & Damper Unit (x2) | C099 | Suspension Assembly – Full Car | 10
E180 | C066 | Rear Upright & Hub Assembly (x2) | C099 | Suspension Assembly – Full Car | 14
E181 | C067 | Rear Anti-Roll Bar | C099 | Suspension Assembly – Full Car | 4
E182 | C099 | Suspension Assembly – Full Car | C100 | Aero & Bodywork Installation | 16
E183 | C068 | Front Wing Mainplane | C100 | Aero & Bodywork Installation | 40
E184 | C069 | Front Wing Flap Cascade Elements (x4) | C100 | Aero & Bodywork Installation | 20
E185 | C070 | Nose Cone (crash structure) | C100 | Aero & Bodywork Installation | 24
E186 | C071 | Bargeboard / Vane Package | C100 | Aero & Bodywork Installation | 28
E187 | C072 | Floor & Skid Block Assembly | C100 | Aero & Bodywork Installation | 36
E188 | C073 | Rear Wing Mainplane | C100 | Aero & Bodywork Installation | 30
E189 | C074 | DRS Flap (Drag Reduction System) | C100 | Aero & Bodywork Installation | 12
E190 | C075 | Beam Wing | C100 | Aero & Bodywork Installation | 14
E191 | C076 | Diffuser | C100 | Aero & Bodywork Installation | 28
E192 | C099 | Suspension Assembly – Full Car | C101 | Brakes, Wheels & Tyre Fitting | 16
E193 | C082 | Carbon Brake Discs – Front (x2) | C101 | Brakes, Wheels & Tyre Fitting | 16
E194 | C083 | Carbon Brake Discs – Rear (x2) | C101 | Brakes, Wheels & Tyre Fitting | 14
E195 | C084 | Brake Calipers – Front (x2) | C101 | Brakes, Wheels & Tyre Fitting | 10
E196 | C085 | Brake Calipers – Rear (x2) | C101 | Brakes, Wheels & Tyre Fitting | 10
E197 | C086 | Brake Ducts & Cooling Scoops (x4) | C101 | Brakes, Wheels & Tyre Fitting | 8
E198 | C087 | Master Cylinders & Brake-by-Wire ECU | C101 | Brakes, Wheels & Tyre Fitting | 10
E199 | C088 | Forged Magnesium Wheels – Front (x2) | C101 | Brakes, Wheels & Tyre Fitting | 8
E200 | C089 | Forged Magnesium Wheels – Rear (x2) | C101 | Brakes, Wheels & Tyre Fitting | 8
E201 | C090 | Pirelli P Zero Tyres – set (4) | C101 | Brakes, Wheels & Tyre Fitting | 2
E202 | C099 | Suspension Assembly – Full Car | C102 | Cockpit, Safety & Electronics Commissioning | 16
E203 | C091 | Halo Titanium Structure | C102 | Cockpit, Safety & Electronics Commissioning | 16
E204 | C092 | Driver Seat (custom moulded) | C102 | Cockpit, Safety & Electronics Commissioning | 12
E205 | C093 | Steering Wheel & Column | C102 | Cockpit, Safety & Electronics Commissioning | 20
E206 | C094 | Safety Harness (6-point) | C102 | Cockpit, Safety & Electronics Commissioning | 2
E207 | C095 | Fire Suppression System | C102 | Cockpit, Safety & Electronics Commissioning | 4
E208 | C096 | Drink System & Helmet Cooling | C102 | Cockpit, Safety & Electronics Commissioning | 3
E209 | C050 | Wiring Loom (PU section) | C102 | Cockpit, Safety & Electronics Commissioning | 16
E210 | C051 | Sensors Array (temp/pressure/speed – PU) | C102 | Cockpit, Safety & Electronics Commissioning | 10
E211 | C097 | PU Installation into Chassis | C103 | Full Car Systems Check & Sign-Off | 24
E212 | C098 | Gearbox Mating to PU | C103 | Full Car Systems Check & Sign-Off | 12
E213 | C099 | Suspension Assembly – Full Car | C103 | Full Car Systems Check & Sign-Off | 16
E214 | C100 | Aero & Bodywork Installation | C103 | Full Car Systems Check & Sign-Off | 20
E215 | C101 | Brakes, Wheels & Tyre Fitting | C103 | Full Car Systems Check & Sign-Off | 8
E216 | C102 | Cockpit, Safety & Electronics Commissioning | C103 | Full Car Systems Check & Sign-Off | 10

## Summary_Stats
Dataset Summary – Honda RA621H F1 Assembly
Metric | Value | Metric | Value
Total Components (Nodes) | 103 | Total Assembly Edges | 216
Critical Path Components | 52 | Non-Critical Components | 51
Total Assembly Duration (hrs) | 1032 | Estimated Total Duration (hrs) | 1485
Total Subsystems | 19 | Unique Materials | 20+
Root Nodes (no deps) | 16 | Leaf Node (Final Sign-Off) | C103
Subsystem Breakdown
Subsystem | # Components | Total Duration (hrs) | Color Code
ICE – Internal Combustion Engine | 15 | 254 | #CC0000
Turbocharger System | 9 | 114 | #E65100
Hybrid – MGU-H | 5 | 68 | #6A1B9A
Hybrid – MGU-K | 5 | 58 | #1565C0
Energy Store (ES) | 4 | 58 | #2E7D32
Lubrication System | 4 | 24 | #5D4037
Cooling System | 3 | 22 | #00695C
Fuel System | 3 | 22 | #F57F17
Electronics & Control | 3 | 34 | #37474F
Chassis & Monocoque | 4 | 132 | #424242
Suspension – Front | 6 | 56 | #880E4F
Suspension – Rear | 6 | 58 | #AD1457
Aerodynamics – Front | 5 | 148 | #0277BD
Aerodynamics – Rear | 4 | 84 | #01579B
Gearbox & Drivetrain | 5 | 112 | #4A148C
Braking System | 6 | 68 | #B71C1C
Wheels & Tyres | 3 | 18 | #33691E
Cockpit & Safety | 6 | 57 | #006064
Final Assembly | 7 | 98 | #212121